## Status Report
Status Report for Team 3 - Orderbook Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-10 | Overall Status: | Green
Contact: | Zeenat | Explanation: | Working through main ideas of project.
Prepared By: | Zeenat
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Zeenat (Lead) | reviewed aspects of order books and went over more requirements for the project
Buchi (frontend) | went over using github for the project. Specifically branches
Anmol(backend) | reviewed aspects of order books and went over more requirements for the project throu
Eric | out sick
All | went over the required diagrams and flowcharts needed for the project
ID # | Key Issues | Action Plan |  |  | Status
1 | figuring out how the entities are going to be populated | ask instructer |  |  | Open
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | NA
Back-end |  | N/A
Business logic |  | N/A
Front-end |  | N/A
Testing |  | N/A
Presentation |  | N/A
Reviewing requirements |  | Average |  | waiting on answer