## Status Report
Status Report for Team 3 - Orderbook Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-10 | Overall Status: | Green
Contact: | Zeenat | Explanation:
Prepared By: | Zeenat
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Zeenat (Lead) | continued to work on the ERD diagram and Worked through more design
Buchi (frontend) | created ERD diagram and walked thorugh more project design
Anmol(backend) | worked through system requirements and designprocess
Eric | out sick
All | went over the required diagrams and flowcharts needed for the project
ID # | Key Issues | Action Plan |  |  | Status
1 | Thinking about the logic that goes into the backend | research more into how matching systems work |  |  | Open
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 90% |  | Set up project, talked through the technology
Back-end |  | 5% |  | Went through the logic
Business logic |  | 0%
Front-end |  | 5% |  | Plan on working on wireframes
Testing |  | 0%
Presentation |  | 0%
Reviewing requirements |  | 80%