## Status Report
Status Report for Team 3 - Orderbook Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-14 | Overall Status: | Green
Contact: | Buchi | Explanation:
Prepared By: | Buchi
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Zeenat (Frontend) | Completed wireframes and UML diagrams
Buchi (Lead) | Completed High Level Overiew and ERD diagram
Anmol(Backend) | Completed system requirements
Eric (Backend) | Completed data dictorinary
ID # | Key Issues | Action Plan |  |  | Status
1 | Figuring out how matching engine would be implemented | trial and research |  |  | in-progress
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 95% |  | created project skeleton
Back-end |  | 7% |  | went through UML diagram
Business logic |  | 0%
Front-end |  | 8% |  | created wireframes
Testing |  | 0%
Presentation |  | 0%
Reviewing requirements |  | 80%